| CHANGIA DIGITAL FUNDRAISING & CONTRIBUTION PLATFORM | Prepared for: Dr. Msuya Date: 21 August 2026 Status: Confidential |
| --- | --- |

PROJECT STATUS REPORT

Development progress, next phase and delivery timeline

Summary — Stage 1 (Core Platform) is complete and has been tested as agreed. Work is now moving into Stage 2 (Campaigns & Sharing). As agreed, the platform is being delivered in two development stages before launch; the third feature will follow after go-live.

PROGRESS OVERVIEW

| COMPLETED — STAGE 1 – Secure sign-in with separate access levels for administrators and managers – Organization dashboard for managing the platform in one place – Donor contact system — add, organize and tag supporters – Core website pages: Home, About, Contact, FAQ, Privacy, Terms – Finalized design in the agreed brand colours | NEXT — STAGE 2 – Creation and management of fundraising campaigns – Shareable campaign links, QR codes and WhatsApp/SMS/email distribution – Public campaign page where donors can view and contribute – Automatic receipts and live progress tracking |
| --- | --- |

PROJECT TIMELINE

| STAGE | DESCRIPTION | STATUS | TARGET |
| --- | --- | --- | --- |
| Stage 1 | Core Platform & Donor Pool | ✓ Complete | 21 August 2026 |
| Stage 2 | Campaign Creation & Link Distribution | In progress | Now – mid-September 2026 |
| Stage 3 | User Acceptance Testing, Deployment & Launch | Upcoming | Late September 2026 |
| Stage 4 | Instant Push Donation module | Post-launch | Scheduled after go-live |

OPEN ITEMS & DECISIONS NEEDED

1 Platform name. "Changia" is currently the working name built into the system. Dr. Msuya has asked for a Swahili name (one or two words) for the public-facing brand — directions discussed include Jamii Yangu and Msalamia Mwema. A separate naming proposal is attached for review; a decision is best made now, before the platform goes live. 2 Production hosting. The platform has not yet been deployed to a live hosting environment — it is currently running in a development setting. Deployment is planned as part of Stage 3 (Testing & Go-Live). 3 Accommodation cost. Dr. Msuya has arranged to cover the team's accommodation for this engagement, TZS 35,000 each via two payment control numbers — 994462516209 (Mr. Mkori) and 994462516211 — for a total of TZS 70,000. Received and acknowledged with thanks. 4 Third feature timing. As agreed, the platform is being delivered in two development stages before launch. Instant Push Donations (Stage 4) will be developed after go-live, once real usage from donors and managers can inform its design.

| PREPARED BY Changia Development Team | ACKNOWLEDGED BY Dr. Msuya |
| --- | --- |